SHALA GLOBAL LTD

This is a proposal about Shala Global Ltd seeking Ksh 3 million to establish a tree nursery at my farm and do climate resilient framing through irrigation

SHELA GLOBAL

LTD

SHALA GLOBAL LTD

This is a proposal about Shala Global Ltd seeking Ksh 3 million to establish a tree nursery at my farm and do climate resilient framing through irrigation

SHELA GLOBAL

LTD

CONTACTS :

0704104906

Cererew@gmail.com

TABLE OF CONTENTS

1.1: Background and Rationale
A background on climate change impacts on local agriculture and the urgent need for tree planting and climate-smart farming solutions on smallholder farms.

1.2: Problem Statement
The environmental degradation, low rainfall, and poor crop yields affecting the farm and the surrounding community, necessitating a sustainable response.

1.3: Objectives of the Project
Specific, measurable goals such as establishing a tree nursery, implementing drip irrigation, increasing soil moisture retention, and enhancing climate resilience.

1.4: Project Description and Activities
The step-by-step activities, including land preparation, nursery setup, sourcing seedlings, installing irrigation infrastructure, and training.

1.5: Expected Outcomes and Impact
Anticipated results like the number of trees planted, improved crop yields, and benefits to soil health, biodiversity, and local microclimates.

1.6: Target Beneficiaries
Who will benefit — e.g., Shala Global Ltd’s farm workers, neighboring smallholder farmers, and local youth engaged in tree planting.

1.7: Sustainability Plan
Strategies for maintaining the nursery and irrigation system post-funding — including income from seedling sales and reinvestment from farm proceeds.

1.8: Monitoring and Evaluation (M&E)
How progress will be tracked, including indicators such as number of trees propagated, hectares irrigated, and crop productivity metrics.

1.9: Work Plan and Timeline
A Quarterly breakdown of activities over a 12-month period — e.g., Q1: nursery setup and seedbed prep; Q2: irrigation installation and seedling growth; Q3: tree planting; Q4: monitoring and reporting.

1.10: Budget Plan and Financial Breakdown

The Ksh 3 million allocation, including costs for nursery equipment, irrigation systems (pipes, tanks, pumps), labor, training, and monitoring tools.

1.1: BACKGROUND AND RATIONALE

Climate change poses a significant threat to agricultural productivity and food security, particularly in regions that rely heavily on rain-fed farming. In Kenya, prolonged droughts, erratic rainfall, rising temperatures, and land degradation have become increasingly common, making it difficult for smallholder farmers to maintain consistent yields. These adverse climate patterns have led to poor harvests, loss of soil fertility, increased pests and diseases, and overall reduced income for farming households.

Shala Global Ltd, situated in a semi-arid region, has experienced firsthand the challenges of declining rainfall and diminishing soil productivity. The farm’s dependency on natural weather patterns has made it highly vulnerable to climate shocks, threatening both agricultural output and livelihoods. The urgent need to adapt to these environmental changes has prompted the company to explore sustainable and resilient farming methods that not only enhance productivity but also contribute to environmental restoration.

Establishing a tree nursery on the farm aligns with Kenya’s national and global climate action commitments, including the 15 billion tree campaign and the United Nations Sustainable Development Goals (SDGs), particularly Goal 13 (Climate Action) and Goal 15 (Life on Land). Trees play a crucial role in restoring degraded land, improving soil structure, enhancing biodiversity, and increasing rainfall infiltration. When integrated with climate-smart agriculture — such as efficient irrigation systems — tree planting becomes a powerful strategy for both mitigation and adaptation.

By developing a tree nursery and implementing climate-resilient farming through irrigation, Shala Global Ltd aims to build a model for smallholder farmers that enhances sustainability, ensures food security, and promotes local environmental conservation. This approach will not only increase the farm’s productivity but also serve as a community-based learning center for nature-based solutions in agriculture.

1.2: PROBLEM STATEMENT

Shala Global Ltd operates in an area increasingly affected by the adverse impacts of climate change, particularly environmental degradation and declining agricultural productivity. Over the past five years, the region has experienced a marked reduction in rainfall, with prolonged dry spells and unpredictable weather patterns becoming the norm. These climatic shifts have resulted in chronic water shortages, leading to reduced soil moisture, increased crop failure, and limited planting seasons.

The farm and its surrounding community face severe land degradation due to deforestation, overcultivation, and erosion. The absence of adequate tree cover has further worsened the situation by contributing to the loss of topsoil, reduced water infiltration, and a rise in surface temperatures. Traditional rain-fed agriculture is no longer reliable, and farmers are struggling to produce enough food for their families or to generate sufficient income from their farms.

Shala Global Ltd has recorded significantly lower crop yields, with staple crops such as maize, beans, and vegetables performing below average due to insufficient water and poor soil health. Without access to sustainable irrigation systems, farmers are left vulnerable, and many have resorted to unsustainable coping mechanisms, including overuse of chemical inputs and abandoning farming altogether.

This situation calls for an urgent, sustainable response that addresses both the immediate and long-term challenges facing the region. By establishing a tree nursery and introducing climate-resilient irrigation systems, Shala Global Ltd seeks to reverse environmental degradation, improve water efficiency, and restore agricultural productivity. This intervention will not only transform the farm into a climate-smart model but also create a ripple effect of resilience across the neighboring farming communities.

1.3: OBJECTIVES OF THE PROJECT

The primary objective of this project by Shala Global Ltd is to enhance climate resilience and improve agricultural productivity through the establishment of a tree nursery and the implementation of a sustainable irrigation system. The project aims to create a model of climate-smart agriculture that can be replicated by other smallholder farmers in the region. The specific, measurable objectives of the project are as follows:

- Establish a Tree Nursery with a Capacity of 50,000 Seedlings per Year

  - Develop a fully functional nursery to propagate indigenous and fruit tree species for on-farm use and distribution to surrounding communities.

  - Target to plant at least 30,000 trees on the farm and distribute 20,000 seedlings to neighboring smallholders annually.

- Install a Climate-Resilient Drip Irrigation System Covering 5 Acres

  - Procure and install water tanks, pipes, pumps, and drip lines to support efficient irrigation.

  - Ensure year-round water supply for crops and nursery seedlings, reducing dependency on rainfall.

- Improve Soil Moisture Retention and Reduce Land Degradation

  - Integrate agroforestry practices with mulching, composting, and minimal tillage to enhance soil health.

  - Increase soil moisture levels by at least 30% within the first year of implementation.

- Enhance Farm Productivity by 50% Within Two Planting Seasons

  - Increase yields of selected crops such as vegetables, legumes, and fruits through reliable water supply and improved soil fertility.

- Create Awareness and Train at Least 100 Local Farmers on Climate-Smart Agriculture

  - Conduct on-site demonstration sessions and workshops to build local capacity on tree planting, nursery management, and irrigation techniques.

- Contribute to Local Reforestation and Climate Action Efforts

  - Support Kenya’s national tree growing initiative and SDGs by promoting sustainable land management and biodiversity restoration.

These objectives are designed to ensure environmental, economic, and social sustainability while building long-term resilience against the effects of climate change.

1.4: PROJECT DESCRIPTION AND ACTIVITIES

The proposed project by Shala Global Ltd aims to establish a comprehensive tree nursery and climate-resilient irrigation system on its farm, creating a scalable model for sustainable agriculture in the face of climate change. The project will be implemented in sequential phases over a 12-month period. Below is a detailed outline of the planned activities:

### Phase 1: Land Preparation (Month 1–2)

- Site Identification and Clearing: Select and clear suitable land (approximately 1 acre) for the tree nursery and 5 acres for irrigated farming.

- Soil Testing and Analysis: Conduct soil tests to determine nutrient composition and inform composting and soil conditioning strategies.

- Nursery Bed Design: Construct shaded nursery beds with appropriate drainage systems and pathways.

### Phase 2: Nursery Establishment (Month 2–4)

- Procurement of Inputs: Acquire polythene tubes, germination trays, organic compost, topsoil, and shade nets.

- Seed Collection and Sourcing: Obtain certified seeds and seedlings of drought-tolerant indigenous and fruit tree species from KFS-approved suppliers.

- Seedling Propagation: Begin germination, transplanting, and routine maintenance (watering, weeding, thinning, and disease control).

- Record-Keeping: Set up a tracking system for species type, germination rate, survival rate, and planting schedules.

### Phase 3: Installation of Irrigation System (Month 3–5)

- Water Source Development: Drill or improve an existing borehole, or install water harvesting structures to support year-round irrigation.

- Procurement and Installation: Purchase and lay out drip irrigation pipes, tanks, filters, solar/water pumps, and control valves.

- System Testing and Calibration: Ensure water flows uniformly to all parts of the farm and nursery beds and train technical staff on maintenance.

### Phase 4: Tree Planting and Climate-Resilient Farming (Month 5–8)

- On-Farm Tree Planting: Begin transplanting seedlings from the nursery to designated areas on the farm, following agroforestry principles (e.g., alley cropping, windbreaks).

- Community Distribution: Organize targeted seedling distribution to smallholder farmers and community-based organizations.

- Climate-Smart Cropping: Grow water-efficient and drought-tolerant crops under the irrigation system, integrating soil conservation practices like mulching and cover cropping.

### Phase 5: Capacity Building and Community Engagement (Month 6–10)

- Farmer Training Sessions: Conduct training workshops for at least 100 farmers on nursery management, tree planting techniques, drip irrigation, and climate-smart agriculture.

- Field Demonstrations: Set up demo plots to showcase integrated farming systems, encouraging adoption by surrounding communities.

### Phase 6: Monitoring, Evaluation, and Documentation (Month 10–12)

- Data Collection: Monitor seedling survival rates, crop yield increases, water usage efficiency, and soil moisture levels.

- Impact Assessment: Evaluate the economic and ecological benefits of the intervention, including reforestation and improved livelihoods.

- Reporting and Knowledge Sharing: Compile reports, case studies, and photo documentation to share with partners, funders, and stakeholders.

This structured approach ensures that the project not only delivers tangible environmental and economic outcomes but also builds local capacity for long-term sustainability.

1.5: EXPECTED OUTCOMES AND IMPACT

The implementation of Shala Global Ltd’s climate-resilient tree nursery and irrigation project is expected to yield transformative results for the farm and the wider community. By integrating reforestation with sustainable agriculture, the project will deliver measurable environmental, economic, and social benefits. The key anticipated outcomes and impacts are as follows:

### Expected Outcomes:

- Establishment of a Tree Nursery Producing 50,000 Seedlings Annually

  - The nursery will propagate a mix of indigenous, fruit, and agroforestry tree species.

  - At least 30,000 trees will be planted annually on the farm, with 20,000 distributed to local farmers and institutions for landscape restoration.

- Installation of a Drip Irrigation System on 5 Acres

  - Efficient irrigation will ensure year-round water availability for crops and seedlings, reducing the farm’s dependence on erratic rainfall.

  - Water use efficiency will improve by over 60%, lowering overall water consumption while boosting productivity.

- Improved Crop Yields by at Least 50% Within Two Seasons

  - Consistent irrigation and improved soil management will increase the productivity of food and horticultural crops.

  - This will translate into greater food security and higher incomes for the farm and potentially for neighboring smallholders replicating the model.

- Soil Health Improvement Across the Farm

  - Integration of organic compost, mulching, and agroforestry will improve soil structure, organic matter content, and moisture retention by over 30%.

  - Reduced erosion and increased nutrient cycling will restore long-term land fertility.

- Biodiversity Enhancement and Microclimate Improvement

  - The increase in tree cover will attract pollinators, birds, and beneficial insects, enhancing farm biodiversity.

  - Shade and windbreak trees will contribute to microclimate stabilization, lowering surface temperatures and reducing evapotranspiration.

- Capacity Building of 100+ Local Farmers

  - Through practical training and demonstration plots, the project will empower local farmers with skills in nursery management, irrigation use, and sustainable land management.

### Broader Impact:

- Environmental: Reforestation will contribute to carbon sequestration, reduce land degradation, and help mitigate the effects of climate change.

- Economic: Increased agricultural productivity and seedling sales will boost income generation for both Shala Global Ltd and participating farmers.

- Social: The project will promote food security, community resilience, and knowledge-sharing, particularly among youth and women interested in agribusiness and conservation.

In sum, the project will position Shala Global Ltd as a champion of climate-smart agriculture and environmental stewardship while setting a replicable precedent for sustainable rural development.

1.6: TARGET BENEFICIARIES

The proposed project by Shala Global Ltd is designed to deliver direct and indirect benefits to a wide range of stakeholders, with a strong focus on inclusivity, local empowerment, and long-term community impact. The key target beneficiaries include:

### 1. Shala Global Ltd Farm Workers

- The farm’s existing workforce will benefit from increased employment opportunities during land preparation, nursery operations, irrigation setup, and tree planting activities.

- Workers will also receive training in nursery management, drip irrigation techniques, and climate-smart farming, improving their skills and income potential.

### 2. Neighboring Smallholder Farmers

- At least 100 smallholder farmers within the surrounding community will be trained in agroforestry, seedling care, soil conservation, and efficient irrigation practices.

- These farmers will receive free or subsidized tree seedlings to plant on their own land, contributing to landscape restoration and diversified livelihoods.

- Improved access to knowledge and planting materials will enable them to increase crop yields and build climate resilience.

### 3. Local Youth and Women Groups

- Youths will be engaged in tree nursery work, planting, watering, and general maintenance activities, giving them hands-on experience in green jobs.

- Women groups and youth groups will be empowered through targeted training sessions and potentially involved in seedling distribution, compost production, and small-scale agri-enterprises.

### 4. Local Schools and Institutions

- Through outreach and collaboration, nearby schools and institutions will benefit from seedlings and training materials, encouraging the integration of environmental conservation into school programs and tree planting on campuses.

### 5. The Broader Community and Environment

- As tree cover increases, the entire region will benefit from improved air quality, better rainfall patterns, restored soil health, and moderated local temperatures.

- The project will contribute to regional and national goals for forest cover increase, food security, and climate action, especially under Kenya’s 15 Billion Trees Initiative and Vision 2030 goals.

By targeting these diverse groups, the project ensures inclusive participation, knowledge transfer, and shared ownership — laying the foundation for a sustainable, community-driven climate adaptation model.

1.7: SUSTAINABILITY PLAN

Shala Global Ltd is committed to ensuring that the tree nursery and climate-resilient farming systems established through this project remain productive, impactful, and financially viable long after the initial funding phase. The sustainability strategy is built around four core pillars: financial self-reliance, operational efficiency, community ownership, and environmental stewardship.

### 1. Income Generation from Seedling Sales

- The tree nursery will produce approximately 50,000 seedlings annually, including indigenous, fruit, and agroforestry species.

- A portion of these seedlings will be sold to individuals, schools, NGOs, county governments, and corporate tree planting programs at affordable prices.

- Revenue from these sales will be reinvested into nursery operations, including labor, potting materials, shading structures, and expansion.

### 2. Reinvestment of Farm Proceeds

- Improved crop yields through irrigation and agroforestry integration will increase farm revenues.

- A portion of the profits from food and horticultural production will be allocated annually to maintain and expand the irrigation system, purchase new components, and support agronomic inputs.

- Shala Global Ltd will create a climate resilience reserve fund from farm income to ensure continuous investment in climate-smart practices.

### 3. Community and Farmer Engagement

- Training and mentorship provided to neighboring farmers will encourage local adoption and ownership of the tree planting and irrigation initiatives.

- Participating farmers will be encouraged to contribute in-kind support (e.g., labor, compost, pots) or adopt their own mini-nurseries, multiplying the project’s impact.

- Collaborative networks with farmer groups and women/youth cooperatives will support peer-led learning and reduce reliance on external support.

### 4. Technical Maintenance and Expansion

- A dedicated nursery and irrigation technician will be trained to maintain equipment, monitor water flow, and provide troubleshooting support.

- Shala Global Ltd will explore solar-powered water pumping systems to reduce long-term energy costs and improve environmental efficiency.

- Regular monitoring and evaluation will ensure the infrastructure remains functional, effective, and scalable.

### 5. Strategic Partnerships and Policy Alignment

- The project will seek collaboration with county agricultural and forestry offices, NGOs, and environmental initiatives to access ongoing technical support, knowledge exchange, and joint programming.

- Alignment with Kenya’s national reforestation, climate adaptation, and food security strategies will open up opportunities for future public-private partnerships and co-financing.

Through this well-structured sustainability plan, Shala Global Ltd aims to build a resilient agroforestry and irrigation model that not only supports its own operations but also drives green growth and environmental restoration across the region.

1.8: MONITORING AND EVALUATION (M&E)

To ensure effective implementation and accountability, Shala Global Ltd will establish a robust Monitoring and Evaluation (M&E) framework that tracks project progress, measures results, and informs adaptive management. The M&E plan will be participatory, results-oriented, and aligned with the project's objectives.

### Monitoring Framework

Monitoring will be conducted continuously throughout the project lifecycle by a dedicated team, with quarterly reviews and annual evaluations. Progress will be tracked using both quantitative and qualitative indicators.

### Key Performance Indicators (KPIs)

| Indicator | Target | Measurement Tool |
| --- | --- | --- |
| Number of seedlings propagated | 50,000 annually | Nursery records, seedling inventory |
| Number of trees planted | 30,000 on-farm; 20,000 off-farm | Field planting logs, GPS mapping |
| Hectares under irrigation | 5 hectares | Irrigation layout plans, visual inspections |
| Increase in crop yields | 50% improvement over two seasons | Yield records, before-and-after comparisons |
| Soil moisture retention | 30% increase | Soil moisture sensors, field sampling |
| Number of farmers trained | 100+ | Attendance lists, pre/post-training surveys |
| Youth engaged in project activities | 40+ | Payroll records, training reports |
| Income from seedling sales | Minimum Ksh 500,000/year | Sales receipts, income statements |

### Evaluation Approach

- Baseline Assessment:
Conducted at project inception to establish benchmarks for key indicators such as crop yields, tree cover, soil condition, and water usage.

- Mid-term Review:
Conducted at the 6-month mark to assess progress, identify challenges, and adjust implementation strategies as needed.

- Endline Evaluation:
At project close, a comprehensive evaluation will assess outcomes against targets and document lessons learned for scaling and replication.

### Data Collection Methods

- Field observations and photo documentation

- GPS mapping and digital data entry tools

- Farmer interviews and focus group discussions

- Monthly project reports and financial tracking

- Soil and crop health testing using simple field kits

### Reporting and Feedback

Findings from M&E activities will be compiled into regular reports shared with stakeholders, funders, and local partners. Feedback loops will be established with farm workers and community members to promote continuous improvement and local ownership.

This rigorous M&E approach will ensure transparency, accountability, and measurable success, while also building an evidence base for scaling the project across other regions.

1.9: WORK PLAN AND TIMELINE

The implementation of Shala Global Ltd’s tree nursery and climate-resilient farming project will follow a structured 12-month work plan. Activities are organized into quarterly phases to ensure smooth execution, efficient resource use, and alignment with seasonal cycles for maximum impact.

### Quarter 1 (Month 1–3): Nursery Setup and Land Preparation

- Activity 1.1: Land clearing and preparation for nursery and farm plot (1 acre for nursery, 5 acres for irrigation)

- Activity 1.2: Construction of nursery infrastructure — shade nets, seedbeds, potting areas, fencing

- Activity 1.3: Procurement of seedling inputs — seeds, polythene tubes, organic compost

- Activity 1.4: Training of staff on nursery management and seedling care

- Activity 1.5: Start propagation of 50,000 seedlings (fruit trees, indigenous trees, fast-growing species)

### Quarter 2 (Month 4–6): Irrigation Setup and Seedling Development

- Activity 2.1: Install drip irrigation system (targeting 5 hectares) — pipes, tanks, filtration units

- Activity 2.2: Establish composting unit for organic farm inputs

- Activity 2.3: Ongoing maintenance of seedlings — watering, thinning, disease management

- Activity 2.4: Training sessions for farm staff and neighboring farmers on drip irrigation and soil health

- Activity 2.5: Community outreach and engagement to recruit tree planting partners

### Quarter 3 (Month 7–9): Tree Planting and Farm Diversification

- Activity 3.1: Transplant 30,000 seedlings on Shala Global farm (boundary, alley cropping, windbreaks)

- Activity 3.2: Distribute 20,000 seedlings to smallholder farmers, schools, and local institutions

- Activity 3.3: Plant climate-resilient food crops under irrigation (vegetables, legumes, cereals)

- Activity 3.4: Conduct refresher training on agroforestry, irrigation scheduling, and post-planting care

- Activity 3.5: Mid-term review and documentation of progress

### Quarter 4 (Month 10–12): Monitoring, Harvesting, and Reporting

- Activity 4.1: Monitor tree survival rates, crop yields, and irrigation system performance

- Activity 4.2: Conduct community feedback sessions and success story documentation

- Activity 4.3: Prepare final project report — outcomes, lessons learned, and recommendations

- Activity 4.4: Launch seedling sales strategy and marketing for sustainability

- Activity 4.5: Explore partnerships for future scaling and replication

This quarterly plan provides a clear and results-oriented roadmap for achieving the project’s climate adaptation, livelihood enhancement, and environmental restoration goals within one year.

1.10: BUDGET PLAN AND FINANCIAL BREAKDOWN

The following table provides a detailed financial breakdown of the Ksh 3 million allocated for the establishment of the tree nursery, climate-resilient farming through irrigation, and related project activities.

| Budget Item | Description | Estimated Cost (Ksh) |
| --- | --- | --- |
| 1. Nursery Setup |  |  |
| Nursery equipment (seed trays, pots, compost) | Purchase of seed trays, polythene tubes, and organic compost for seedling propagation | 250,000 |
| Construction of nursery infrastructure | Construction of shade netting, seedbeds, and fencing | 200,000 |
| Seedling inputs (seeds and fertilizers) | Procurement of tree seeds (fruit trees, indigenous species), fertilizers | 150,000 |
| 2. Irrigation System |  |  |
| Drip irrigation system (pipes, filters, pumps) | Installation of a 5-hectare drip irrigation system, including pipes, pumps, and filtration units | 600,000 |
| Water storage tanks | Purchase and installation of tanks for water storage (capacity for 5 hectares) | 200,000 |
| 3. Labor and Personnel |  |  |
| Labor for nursery and irrigation setup | Hiring of casual laborers for land clearing, irrigation installation, and nursery setup | 250,000 |
| 4. Training and Capacity Building |  |  |
| Training for farm staff and local farmers | Training on agroforestry, irrigation, and nursery management | 200,000 |
| 5. Monitoring and Evaluation (M&E) |  |  |
| Monitoring tools (soil moisture sensors, GPS tools) | Purchase of tools for field monitoring (soil moisture, GPS for planting mapping) | 150,000 |
| M&E staff costs | Hiring and training of M&E staff for continuous monitoring and data collection | 150,000 |
| 6. Miscellaneous and Contingency |  |  |
| Miscellaneous expenses (transport, communication) | Miscellaneous costs for logistics, communication, and unforeseen expenses | 100,000 |
| Total Budget |  | 3,000,000 |

This budget plan ensures that all necessary components of the tree nursery, irrigation system, and training initiatives are properly funded. The allocation reflects a balanced investment in infrastructure, human resources, and tools to maximize the project's success and long-term sustainability.