OWIT KENYA

OWITKENYA PROPOSAL  membership@owitnairobi.org  0704104906

ORGANISATION OF WOMEN IN INTERNATIONAL TRADE PROPOSAL

### TABLE OF CONTENTS

### 1.1 Background/Introduction

- Empowering Women Through Global Trade: The Legacy and Expansion of OWIT Kenya
A comprehensive overview of OWIT Kenya's journey since its establishment in 2001, its link to the global OWIT network founded in 1989 in the USA, and its role in promoting gender-inclusive trade across Kenya.

- Harnessing Trade as a Tool for Economic Transformation Among Women and Youth
Introduction to the role of OWIT Kenya in aligning women’s economic empowerment with national and continental trade agendas like AfCFTA, Vision 2030, and Kenya’s Export Development Strategy.

### 1.2 Problem Statement/Needs Assessment

- Underrepresentation of Women and Youth in Export Trade in Kenya
A data-driven analysis highlighting the low number of women-led export businesses and the barriers limiting their participation in international markets.

- Lack of Comprehensive Mapping and Visibility of Women Traders Across the Country
An examination of the need for nationwide mapping to identify women engaged or interested in export trade to facilitate targeted interventions.

- Inadequate Institutional Resources to Support Membership Growth and Operations
An outline of OWIT Kenya’s challenges in scaling its reach and impact due to limited administrative and operational funding.

### 1.3 Project Rationale/Justification

- Strengthening Women Exporters to Accelerate Inclusive Economic Development
Justification of why increasing women and youth exporters aligns with Kenya’s economic and gender development goals.

- Positioning OWIT Kenya as a National Anchor Institution for Women in Trade
Explaining why OWIT Kenya is uniquely placed to carry out the mapping, mentorship, and empowerment program due to its national and international linkages.

- Bridging the Gender Gap in International Trade Through Strategic Investments
Argument for funding the Ksh 60 million proposal to create equitable access to export opportunities and build strong trade networks.

- Work Plan: National Mapping, Membership Mobilization, and Exporter Training Rollout
A detailed two-year work plan broken down into key phases such as stakeholder engagement, mapping, capacity building, and exporter pipeline development.

- Budget Plan: Two-Year Financial Projection for Mapping, Operations, and Capacity Building
A Ksh 60 million itemized budget showing allocation for staffing, mapping logistics, training sessions, administration, technology, and outreach.

### 1.1 BACKGROUND/INTRODUCTION

#### Empowering Women Through Global Trade: The Legacy and Expansion of OWIT Kenya

The Organisation of Women in International Trade (OWIT) is a global network that was established in 1989 in the United States of America with the mission of fostering the advancement of women in international trade and business. With 23 active chapters worldwide, OWIT has grown into a formidable force for global economic inclusion and gender equity. It serves as a platform for knowledge exchange, policy influence, and business development, tailored to empower women to thrive in cross-border trade and entrepreneurship.

OWIT Kenya, one of the vibrant chapters under this global umbrella, was officially launched in April 2001 by the United States Embassy in Nairobi. It operates as a registered membership association headquartered at Professional House in Karen, Nairobi. Since its inception, OWIT Kenya has remained steadfast in its commitment to promoting gender-inclusive trade by equipping women with the tools, networks, and platforms necessary to succeed in both regional and global markets.

Over the years, OWIT Kenya has grown to become a respected voice in trade policy discussions and a vital partner in capacity building for women and youth-led enterprises. It has worked collaboratively with government institutions, trade agencies, embassies, development partners, and private sector stakeholders to bridge the gender gap in international trade. Through mentorship, training, and advocacy, OWIT Kenya continues to champion the economic empowerment of women as a catalyst for community and national development.

#### Harnessing Trade as a Tool for Economic Transformation Among Women and Youth

OWIT Kenya views trade not just as a business opportunity, but as a transformative vehicle for inclusive economic development. Recognizing the potential of women and youth as drivers of growth, OWIT Kenya’s programs are designed to reduce barriers that hinder their full participation in global commerce. These barriers include limited access to information, finance, networks, and export readiness training.

The organization’s strategic focus aligns with key national and continental frameworks, including Kenya Vision 2030, the African Continental Free Trade Area (AfCFTA), and the Kenya Export Development and Promotion Strategy. By facilitating the integration of women and youth into formal trade ecosystems, OWIT Kenya aims to contribute to increased household incomes, job creation, poverty reduction, and national competitiveness.

In particular, OWIT Kenya is scaling its efforts to reach women entrepreneurs across all counties through a nationwide mapping initiative. This will not only provide critical data to inform targeted interventions but will also foster the inclusion of underserved regions in trade-related capacity building. The initiative is a proactive response to the need for a coordinated, data-driven approach to women’s economic empowerment through trade.

In its next phase of growth, OWIT Kenya seeks strategic investment and support to deepen its footprint, strengthen institutional capacity, and enroll more women and youth exporters into sustainable global value chains. This grant request will enable OWIT Kenya to operationalize its long-term vision of transforming communities through empowered women traders who lead, influence, and scale their businesses across borders.

### 1.2 PROBLEM STATEMENT/NEEDS ASSESSMENT

#### Underrepresentation of Women and Youth in Export Trade in Kenya

Despite making up over 50% of Kenya’s population and playing a significant role in the country’s micro and small enterprise sector, women and youth remain grossly underrepresented in formal export trade. According to various national and regional studies, less than 20% of Kenyan export businesses are women-owned or women-led. This disparity is driven by a combination of systemic, structural, and socio-economic barriers that restrict access to opportunities within international markets.

Key obstacles include limited access to trade financing, inadequate knowledge of international trade procedures, non-tariff barriers, weak business networks, and minimal participation in trade policy dialogue. For young entrepreneurs, the situation is exacerbated by high unemployment, limited mentorship, and exclusion from high-value value chains. As a result, the potential of women and youth to contribute meaningfully to Kenya’s export growth remains largely untapped, leading to missed opportunities in both income generation and national economic development.

OWIT Kenya recognizes that increasing the number of women and youth exporters is not only a matter of fairness but an economic imperative. Tapping into this underutilized demographic can significantly boost household livelihoods, promote job creation, and contribute to achieving Kenya’s Vision 2030 goals and the broader African Continental Free Trade Area (AfCFTA) aspirations.

#### Lack of Comprehensive Mapping and Visibility of Women Traders Across the Country

One of the biggest challenges hindering effective intervention in women’s trade empowerment is the lack of comprehensive data on women traders across Kenya. Currently, there is no centralized database or mapping mechanism to identify, classify, and track women and youth engaged in trade — particularly those at the micro, small, and medium enterprise (MSME) level who are most likely to benefit from targeted capacity building, financing, and policy support.

This data gap has led to a fragmented approach in supporting women traders, resulting in duplication of efforts, exclusion of rural and marginalized populations, and inefficient resource allocation. Without proper mapping, it becomes difficult to know who the traders are, what sectors they operate in, their level of export-readiness, and what specific barriers they face.

OWIT Kenya proposes a nationwide mapping exercise to identify, register, and assess the needs of women and youth traders in all 47 counties. This initiative will serve as a foundational step for designing evidence-based interventions, building a credible and accessible trade directory, and amplifying the visibility of women entrepreneurs in Kenya’s trade ecosystem.

#### Inadequate Institutional Resources to Support Membership Growth and Operations

As a membership-based organization, OWIT Kenya has demonstrated high-impact outcomes within its operational limits. However, its ability to scale and deliver on its mandate nationwide is constrained by inadequate administrative, operational, and logistical resources. For over two decades, the organization has operated with lean budgets, relying heavily on volunteerism and intermittent donor support.

Critical institutional gaps include limited full-time staff, constrained outreach capacity, outdated data management systems, and insufficient funds for sustained programming and member engagement. This affects OWIT Kenya’s ability to mobilize new members, retain existing ones, offer consistent value-added services, and conduct regular training, mentorship, and advocacy activities.

To unlock its full potential, OWIT Kenya requires strategic investment to build robust institutional systems, scale outreach across counties, and professionalize its operations. Strengthening its administrative and operational backbone is key to transforming the organization into a national anchor for women’s participation in trade and export development.

### 1.3 PROJECT RATIONALE/JUSTIFICATION

#### Strengthening Women Exporters to Accelerate Inclusive Economic Development

Empowering women and youth to participate in international trade is both a social imperative and an economic opportunity for Kenya. Women account for the majority of micro and small enterprises, yet their representation in formal export markets remains disproportionately low. Bridging this gap is critical to achieving Kenya’s long-term development goals under Vision 2030, the Big Four Agenda, the Kenya Export Development and Promotion Strategy (2023–2027), and regional frameworks such as the African Continental Free Trade Area (AfCFTA).

By equipping women and youth with the skills, knowledge, and networks necessary to engage in export trade, OWIT Kenya seeks to unlock new income streams, promote job creation, and drive inclusive growth across counties. Women exporters have a multiplier effect on communities—when women succeed in business, they reinvest in families, education, and health, contributing to poverty reduction and intergenerational progress. Increasing their participation in trade will not only expand Kenya’s export base but also enhance the country’s competitiveness in global markets.

#### Positioning OWIT Kenya as a National Anchor Institution for Women in Trade

OWIT Kenya’s strategic advantage lies in its dual positioning as a local organization with global connections. As a chapter of the Organisation of Women in International Trade (founded in 1989 in the USA), OWIT Kenya has access to an expansive international network of trade professionals, development partners, policy influencers, and mentors. This global reach is complemented by its strong local presence, having been established in Kenya in 2001 with support from the US Embassy.

Over the years, OWIT Kenya has cultivated relationships with key trade stakeholders, including government ministries, regional economic blocs, embassies, and private sector players. Its track record in advocacy, capacity building, and trade facilitation makes it a trusted institution to spearhead the nationwide mapping of women and youth exporters, coordinate tailored mentorship, and implement targeted export-readiness programs.

Given its mandate, credibility, and existing networks, OWIT Kenya is uniquely positioned to act as a national anchor institution for advancing gender-inclusive trade. Its structured membership model and county-based expansion plan make it well-suited to engage diverse women traders and ensure no region is left behind.

#### Bridging the Gender Gap in International Trade Through Strategic Investments

To realize this bold vision, OWIT Kenya is seeking Ksh 60 million over a two-year period. This funding will support three primary pillars:

- Nationwide Mapping of women and youth traders across all 47 counties to create a trade database and inform targeted interventions.

- Administrative and Operational Strengthening to build a solid institutional foundation that can scale outreach, programming, and policy engagement.

- Membership and Exporter Growth through intensive recruitment, mentorship, training, and facilitation into formal export markets.

This investment is not a cost—it is a catalyst for transformational change. It will ensure equitable access to trade opportunities for women and youth, accelerate the implementation of gender-responsive trade policies, and promote Kenya’s sustainable economic development. The funding will enable OWIT Kenya to serve as a scalable model for inclusive trade promotion, and contribute meaningfully to national and continental goals.

In summary, investing in OWIT Kenya is investing in a more inclusive, equitable, and prosperous Kenya.

### 1.9 WORK PLAN: NATIONAL MAPPING, MEMBERSHIP MOBILIZATION, AND EXPORTER TRAINING ROLLOUT

To achieve its goal of empowering women and youth through trade, OWIT Kenya has developed a structured two-year work plan organized into four strategic phases: stakeholder engagement, national mapping, capacity building, and exporter pipeline development. This phased approach ensures efficiency, measurable impact, and national reach.

#### Phase 1: Stakeholder Engagement and Framework Development (Months 1–3)

Objective: Build strategic partnerships and develop tools for effective program rollout.

Key Activities:

- Convene stakeholder meetings with government agencies (Ministry of Trade, Kenya Export Promotion & Branding Agency, county governments), development partners, and private sector trade facilitators.

- Establish a National Coordination Committee to guide implementation.

- Design data collection tools and digital platforms for mapping and registration.

- Sign MOUs with county trade departments and relevant national bodies.

- Launch a national awareness campaign to mobilize support and participation.

Output: Stakeholder engagement reports, signed MOUs, developed tools, and a national project roadmap.

#### Phase 2: Nationwide Mapping and Registration (Months 4–9)

Objective: Identify and profile women and youth engaged or interested in export trade across Kenya’s 47 counties.

Key Activities:

- Recruit and train county-based field officers and enumerators.

- Conduct county-level mapping using digital tools (surveys, GIS mapping, interviews).

- Develop a centralized and searchable database of women and youth traders.

- Classify traders by sector, trade-readiness level, location, and support needs.

- Publish a National Mapping Report with policy and programmatic recommendations.

Output: A comprehensive national database of women and youth traders and a baseline report.

#### Phase 3: Membership Mobilization and Institutional Strengthening (Months 10–18)

Objective: Grow OWIT Kenya’s membership base and strengthen institutional capacity to serve national-level functions.

Key Activities:

- Launch a membership recruitment drive in all 47 counties targeting women and youth.

- Conduct onboarding and orientation for new members.

- Establish or strengthen county chapters and working groups.

- Recruit and train core administrative and program staff.

- Upgrade data systems, communications infrastructure, and member management platforms.

- Develop a sustainability strategy including local fundraising and partnerships.

Output: Expanded and active membership, enhanced organizational systems, and operational capacity.

#### Phase 4: Exporter Capacity Building and Pipeline Development (Months 19–24)

Objective: Build the skills, networks, and confidence of women and youth to participate in export trade.

Key Activities:

- Conduct regional exporter training bootcamps on product certification, export logistics, digital trade, and trade finance.

- Pair emerging exporters with mentors from OWIT’s international network.

- Link traders to opportunities under AfCFTA, EAC, AGOA, and other trade frameworks.

- Organize trade missions, virtual exchanges, and participation in international expos.

- Facilitate access to finance and investment readiness programs.

- Monitor and evaluate outcomes; document success stories and lessons learned.

Output: A pipeline of trained, export-ready women and youth entrepreneurs with international exposure and market linkages.

#### Cross-Cutting Activities (Ongoing throughout the 2 years)

- Media and public relations to promote visibility and impact.

- Monitoring and Evaluation (M&E) to track progress and inform adjustments.

- Reporting and donor engagement.

- Policy advocacy for gender-inclusive trade reforms.

This two-year work plan provides a scalable and sustainable pathway for OWIT Kenya to transform the trade landscape for women and youth across the country. Each phase builds upon the last, ensuring momentum, inclusivity, and measurable success.

### 1.10 Budget Plan: Two-Year Financial Projection for Mapping, Operations, and Capacity Building

To effectively implement the proposed national mapping, membership mobilization, and exporter development program, OWIT Kenya projects a total budget of Ksh 60 million over two years. This budget is strategically allocated to cover key components that are essential to the success and sustainability of the initiative, including staffing, logistics, technology infrastructure, training, administration, and outreach.

Below is an itemized budget breakdown:

#### A. Staffing and Human Resources – Ksh 15,000,000

| Description | Year 1 (KES) | Year 2 (KES) | Total (KES) |
| --- | --- | --- | --- |
| National Program Coordinator | 1,200,000 | 1,200,000 | 2,400,000 |
| Field Enumerators (47 counties) | 2,500,000 | 2,500,000 | 5,000,000 |
| Administrative Support Staff | 1,000,000 | 1,000,000 | 2,000,000 |
| Training Facilitators and Mentors | 2,000,000 | 2,000,000 | 4,000,000 |
| Sub-Total | 6,700,000 | 6,700,000 | 13,400,000 |
| Contingency & Benefits (10%) | 670,000 | 930,000 | 1,600,000 |

#### B. Mapping Logistics and Data Collection – Ksh 12,000,000

| Description | Year 1 | Year 2 | Total |
| --- | --- | --- | --- |
| Field Travel & Transport | 3,000,000 | 2,000,000 | 5,000,000 |
| Mapping Tools & Digital Platforms | 2,000,000 | 500,000 | 2,500,000 |
| Data Management & Analysis | 1,000,000 | 500,000 | 1,500,000 |
| GIS and Visualization Software | 800,000 | 200,000 | 1,000,000 |
| Printing and Stationery | 1,000,000 | 1,000,000 | 2,000,000 |

#### C. Capacity Building and Exporter Training – Ksh 10,000,000

| Description | Year 1 | Year 2 | Total |
| --- | --- | --- | --- |
| Regional Training Bootcamps (5 clusters) | 2,000,000 | 2,000,000 | 4,000,000 |
| Export Readiness Materials & Manuals | 800,000 | 800,000 | 1,600,000 |
| Trade Missions and Exposure Visits | 2,000,000 | 2,000,000 | 4,000,000 |
| Virtual Training Infrastructure | 200,000 | 200,000 | 400,000 |

#### D. Administration and Office Operations – Ksh 9,000,000

| Description | Year 1 | Year 2 | Total |
| --- | --- | --- | --- |
| Office Rent & Utilities (Karen, Nairobi) | 1,500,000 | 1,500,000 | 3,000,000 |
| Office Supplies & Equipment | 1,000,000 | 500,000 | 1,500,000 |
| Communications (Internet, Phone, Printing) | 700,000 | 700,000 | 1,400,000 |
| Project Monitoring & Evaluation | 1,000,000 | 1,000,000 | 2,000,000 |
| Annual Audit & Reporting | 500,000 | 600,000 | 1,100,000 |

#### E. Technology, Branding, ad Outreach – Ksh 8,000,000

| Description | Year 1 | Year 2 | Total |
| --- | --- | --- | --- |
| Website Upgrade & CRM Systems | 1,000,000 | 500,000 | 1,500,000 |
| Social Media Campaigns & PR | 1,000,000 | 1,000,000 | 2,000,000 |
| Branding & Promotional Materials | 1,000,000 | 1,000,000 | 2,000,000 |
| Outreach Events (National/County) | 1,000,000 | 1,000,000 | 2,000,000 |
| Documentation & Success Story Publishing | 250,000 | 250,000 | 500,000 |

#### F. Contingency and Emergency Reserve (5%) – Ksh 6,000,000

To accommodate unforeseen expenses, exchange rate fluctuations, inflation, or expansion needs during implementation.

### Summary Budget Table

| Budget Category | Total Amount (KES) |
| --- | --- |
| Staffing and Human Resources | 15,000,000 |
| Mapping Logistics and Data Collection | 12,000,000 |
| Capacity Building and Exporter Training | 10,000,000 |
| Administration and Office Operations | 9,000,000 |
| Technology, Branding, and Outreach | 8,000,000 |
| Contingency Reserve | 6,000,000 |
| TOTAL | 60,000,000 |

This budget ensures a well-coordinated and high-impact program that strengthens OWIT Kenya’s capacity to deliver its mission while reaching thousands of women and youth across Kenya. The allocation reflects a commitment to transparency, sustainability, and measurable results.