## Slide 1
PROGRAM MANAGEMENT TRAINING
Stakeholder
Management
Identification · Engagement · Communication
for Overall Program Success
Programs succeed or fail based on how well stakeholders are managed.

## Slide 2
AGENDA
01
Who Are Stakeholders?
Definition and why they matter in programs
02
Stakeholder Identification
Techniques to surface all stakeholders
03
Stakeholder Analysis
Power/Interest Grid & prioritisation
04
Engagement Strategies
Tailored approaches by stakeholder type
05
Communication Channels
Right message, right channel, right time
06
Managing Difficult Stakeholders
Conflict, resistance, and recovery
07
Monitoring & Feedback Loops
Keeping engagement alive throughout the program

## Slide 3
01 | Who Are Stakeholders?
Definition: Any individual, group, or organisation that can affect, be affected by, or perceives itself to be affected by a program's objectives, outputs, or outcomes.
Internal
› Program Sponsor
› Project Managers
› Team Members
› PMO
› Finance & Legal
External
› Clients / Beneficiaries
› Vendors & Suppliers
› Regulatory Bodies
› Media
› Community Groups
Interface
› Partner Organisations
› Cross-functional Units
› Government Agencies
› Donor Bodies
› Technical Advisors

## Slide 4
02 | Stakeholder Identification
Use multiple techniques — no single method captures everyone.
Document Review
Review program charter, contracts, org charts, previous lessons learned registers.
Brainstorming Sessions
Multi-disciplinary workshops — ask 'Who wins? Who loses? Who cares?'
Snowball Technique
Ask identified stakeholders: 'Who else should we be talking to?'
RACI Matrix Mapping
Identify Responsible, Accountable, Consulted, and Informed parties across workstreams.
Expert Interviews
One-on-one conversations with subject matter experts and domain leads.
Stakeholder Register
Living document capturing name, role, interest, influence, and engagement level.
⚡ Golden Rule: Identify stakeholders BEFORE planning starts — late discovery creates costly rework and damaged relationships.

## Slide 5
03 | Stakeholder Analysis: Power / Interest Grid
MONITOR
Keep Informed
(Low effort, stay aware)
MANAGE CLOSELY
Key Players
(Maximum engagement)
KEEP SATISFIED
Keep Satisfied
(Meet their needs)
KEEP INFORMED
Show Consideration
(Regular updates)
POWER (Influence)
↑ INTEREST (Concern)
LOW
HIGH
Engagement Strategy by Quadrant
Manage Closely
Partner, co-create, give priority access to info
Keep Satisfied
Regular briefings, address concerns proactively
Keep Informed
Newsletters, public comms, periodic updates
Monitor
Watchlist only — light-touch, no overload

## Slide 6
04 | Stakeholder Engagement Strategies
The Engagement Ladder
5 — Co-Create
Shared ownership of design & decisions
4 — Collaborate
Joint problem-solving and co-design
3 — Involve
Input sought before decisions are made
2 — Consult
Feedback gathered on proposals
1 — Inform
One-way communication of decisions
Key Engagement Principles
Relationship First
Build trust before you need it. Engage early and continuously.
Listen Actively
Engagement is two-way. Stakeholders must feel heard, not managed.
Tailor Approach
Different stakeholders need different frequency and format.
Stay Consistent
Irregular communication erodes trust faster than silence.
Manage Expectations
Overpromise is the fastest path to a hostile stakeholder.

## Slide 7
05 | Communication Channels
Right message · Right channel · Right audience · Right time
Channel | Best For | Frequency | Richness | Notes
Steering Committee Meetings | Sponsors & senior leaders | Monthly / Milestone | ●●●●● | Formal, decision-focused
Program Status Reports | All stakeholders | Weekly / Bi-weekly | ●●●○○ | Written; clear RAG status
One-on-One Meetings | Key influencers | As needed | ●●●●● | Relationship-building
Stakeholder Workshops | Wide groups | Phase gates | ●●●●○ | Co-creation, buy-in
Email Updates / Newsletters | Inform quadrant | Bi-weekly | ●●○○○ | Consistent, scannable
Dashboard / Portal | All levels | Real-time | ●●●○○ | Self-serve; reduces noise
Town Halls / Townhall Calls | Large audiences | Quarterly | ●●●○○ | Broadcast + Q&A
Informal Channels (Slack etc) | Internal teams | Daily | ●●○○○ | Speed; NOT for decisions

## Slide 8
05 | Stakeholder Communication Plan
Every communication should answer five questions:
WHO?
Which stakeholder or group?
WHAT?
What information do they need?
WHEN?
What is the timing and frequency?
HOW?
Which channel or format?
WHY?
What outcome do we want from this comms?
Sample Communication Plan Extract
Stakeholder | Info Need | Channel | Frequency | Owner | Status
Program Sponsor | Progress vs. milestones | Steering Cmte Meeting | Monthly | PM | Active ✓
County Government | Compliance & outcomes | Formal Report | Quarterly | Director | Active ✓
Beneficiary Groups | Program impact & changes | Community Meetings | Bi-monthly | Comms Lead | Active ✓
Vendor Partners | Delivery schedule | Email + Dashboard | Weekly | Procurement | Active ✓
Regulatory Body | Statutory reporting | Formal Submission | As required | Legal | Pending ⚡

## Slide 9
06 | Managing Difficult Stakeholders
The Blocker
Signs:
Escalates issues, vetoes decisions, withholds support
Tactic:
Seek private dialogue first. Uncover the root concern. Involve them in solution design.
The Disengaged
Signs:
Misses meetings, delegates downward, non-responsive
Tactic:
Elevate the stakes. Show them what they risk losing. Engage their motivations directly.
The Vocal Critic
Signs:
Publicly challenges decisions, rallies opposition
Tactic:
Give them a platform — make them a co-creator. Criticism + ownership = advocacy.
The Scope Creeper
Signs:
Constantly adds new demands, expands expectations
Tactic:
Re-ground in charter. Use change control formally. Show impact of additions on timeline.

## Slide 10
07 | Monitoring & Feedback Loops
The 5-Step Stakeholder Engagement Cycle
1
Identify &
Analyse
→
2
Plan
Engagement
→
3
Execute
& Engage
→
4
Monitor &
Evaluate
→
5
Adapt &
Improve
↺ This cycle repeats continuously throughout the full program lifecycle
Key Principle: Stakeholder engagement is NOT a phase — it is a discipline that runs from program initiation through closure.
Monitoring Tools & Techniques
Engagement Heat Map
Visual tracking of engagement level per stakeholder
Issue & Risk Logs
Capture stakeholder-raised risks before they escalate
Satisfaction Surveys
Pulse checks at phase gates; act on every result
Program Dashboard
Real-time visibility; reduces information anxiety

## Slide 11
Common Pitfalls in Stakeholder Management
1
Identifying stakeholders too late in the program
2
Treating all stakeholders the same — one-size comms fails
3
Communicating only when something goes wrong
4
Forgetting hidden or silent stakeholders with veto power
5
Over-communicating to the wrong people (noise fatigue)
6
Using jargon-heavy reports with non-technical audiences
7
Ignoring negative stakeholders instead of engaging them
8
Not updating the stakeholder register as the program evolves
9
Promising outcomes you cannot deliver to gain buy-in
10
No escalation path when stakeholder conflict derails progress

## Slide 12
Key Takeaways
What every program manager must remember about stakeholder management
01
Stakeholder identification is not a one-time task — it is a living process that spans the full program lifecycle.
02
The Power/Interest Grid is your strategic compass. Use it to prioritise where your limited energy goes.
03
Communication is not just reporting — it is the instrument through which trust is built or destroyed.
04
Difficult stakeholders are not the enemy. They are often your most important source of program intelligence.
05
Programs do not fail from lack of plans. They fail when the people who matter are not in the room — or feel like they are not.

## Slide 13
Remember:
"Programs are not delivered by systems.
They are delivered by people.
Manage your stakeholders,
and you manage your program."
Questions & Discussion
Program Management Training · Stakeholder Management for Program Success