## Slide 1
STAKEHOLDER MANAGEMENT · MODULE 2
Applied Scenarios
& Case Studies
Real organisations. Real failures. Your analysis.
🔍 Identify the Failure
💡 Diagnose the Root Cause
✅ Design the Fix
Programs succeed or fail based on how well stakeholders are managed. Let's examine what that looks like in practice.

## Slide 2
How to Use This Module
Each case follows the same structure — designed for group discussion and creative thinking.
01
Read the Case
A real-world scenario is presented — a company, a program, a crisis. Read it carefully before discussing.
02
Spot the Failure
Identify WHAT went wrong. Use your stakeholder framework: identification, analysis, engagement, or communication?
03
Diagnose the Root Cause
Go deeper. WHY did it go wrong? Which bias, structural gap, or leadership failure was the true driver?
04
Design the Fix
What would YOU have done differently? Be specific — name the tool, the timing, and the stakeholder.
05
Answer the Challenge Qs
Each case ends with 3 questions: one analytical, one creative, one provocative. No wrong answers — only unexplored ones.

## Slide 3
01
CASE STUDY
BP
Deepwater
Horizon
2010 · Gulf of Mexico
11
lives lost
87
days spilling
$65B+
total cost
What Happened?
The Deepwater Horizon oil rig exploded in the Gulf of Mexico in April 2010, causing the largest marine oil spill in history. BP had received multiple safety warnings from engineers and contractors in the weeks leading up to the explosion — warnings that were overridden by management under pressure to reduce costs and meet drilling deadlines.
The Stakeholder Failure:
Engineers and safety inspectors flagged critical risks — they were ignored
Regulators (MMS) had a cosy relationship with BP — oversight was absent
Local fishing communities and coastal residents had zero voice in risk decisions
Transocean rig workers were not empowered to halt operations
Shareholders and the public had been given a false picture of BP's safety culture

## Slide 4
Case 01 — BP Deepwater Horizon
Your Challenge: Analyse the Stakeholder Failure
ANALYTICAL
Using the Power/Interest Grid, map the key stakeholders in this crisis. Which quadrant held the most critical failures — and why?
💬 Think about: engineers, regulators, executives, rig workers, coastal communities, shareholders.
CREATIVE
You are BP's Head of Stakeholder Engagement in 2009. Design one intervention that could have prevented the crisis. Be specific about the channel, the audience, and the trigger.
💬 Constraints: You have no new budget. You can only change processes and communication flows.
PROVOCATIVE
BP's CEO Tony Hayward said publicly 'I'd like my life back.' What does this statement reveal about BP's understanding of who their stakeholders actually were?
💬 Consider: Who was the primary audience for this message? Who was the actual audience? What was the effect?
⏱ Group Activity — 15 minutes | Appoint one spokesperson per group to present your answer to Question 2

## Slide 5
02
CASE STUDY
Heathrow
Terminal 5
Opening
2008 · London, UK
500+
flights cancelled
28K
bags lost
£16M
direct losses
What Happened?
Heathrow Terminal 5 opened in March 2008 after a £4.3 billion, 19-year build — one of the UK's largest construction projects. On opening day, the terminal descended into chaos: baggage systems failed, staff couldn't find car parks, check-in agents had not been trained on the new systems. Over 28,000 bags were lost in the first two weeks.
The Stakeholder Failure:
Staff were not involved in the design of operational processes
Training for baggage handlers and check-in agents was inadequate
BAA and British Airways blamed each other — governance was fragmented
Passengers and media were given no warning or contingency information
Staff feedback during testing phases was collected but not acted on

## Slide 6
Case 02 — Heathrow Terminal 5 Opening
Your Challenge: Analyse the Stakeholder Failure
ANALYTICAL
This failure involved internal stakeholders — staff and managers — not external ones. How does the Stakeholder Register fail when it only focuses on external parties? What should BAA's register have included?
💬 Consider: frontline workers, baggage handlers, airline staff, training managers, terminal designers.
CREATIVE
Design a 'Stakeholder Readiness Assessment' for the T5 launch — a checklist that would have caught the gaps before opening day. What are the five non-negotiable items on your list?
💬 Think about: training completion, system testing with end-users, contingency communication plans, car park access, supervisor briefings.
PROVOCATIVE
BAA spent £4.3 billion and 19 years building T5 — but failed to spend adequately on the people who would run it. What does this tell us about how organisations value different types of stakeholders?
💬 Reflect on: Capital vs. human investment. Infrastructure vs. engagement. Technical delivery vs. operational readiness.
⏱ Group Activity — 15 minutes | Each group drafts their Stakeholder Readiness Checklist (Q2) and presents to the room

## Slide 7
03
CASE STUDY
Kodak's
Digital
Blindspot
1975–2012 · Rochester, USA
#1
film market share in 1976
145K
jobs at peak
Ch.11
bankruptcy 2012
What Happened?
Kodak invented the digital camera in 1975 — but buried it. For decades, Kodak dominated photography with its film business. Leadership knew digital would disrupt them but chose to protect existing revenue streams rather than adapt. By 2012, Kodak had filed for bankruptcy, overtaken by companies it once dwarfed.
The Stakeholder Failure:
Customers' shifting needs were observed but not taken seriously
Internal engineers who championed digital were sidelined
Shareholders were never honestly briefed on the digital disruption risk
Film retail partners were over-consulted — locking Kodak in the past
Emerging consumer tech companies were never mapped as competitors-turned-stakeholders

## Slide 8
Case 03 — Kodak's Digital Blindspot
Your Challenge: Analyse the Stakeholder Failure
ANALYTICAL
Kodak's stakeholder register was likely focused on existing partners — film retailers, distributors, printing labs. What stakeholder identification technique would have surfaced the 'disruptive' stakeholders they missed? Explain your reasoning.
💬 Review: Snowball Technique, Expert Interviews, scenario planning, horizon scanning.
CREATIVE
In 1990, you are Kodak's Chief Strategy Officer. You have data showing digital adoption will accelerate. Write a 3-sentence stakeholder communication that honestly tells the board what is coming — without triggering panic or stock collapse.
💬 Consider: language precision, what you reveal vs. withhold, and who else might see this communication.
PROVOCATIVE
Kodak's engineers built the digital camera — and were ignored. In your experience or observation, when organisations silence internal voices, what cultural conditions make this possible? And who bears responsibility?
💬 Connect to: Groupthink (Janis), HiPPO effect, Conformity Bias — concepts from Module 1.
⏱ Group Activity — 15 minutes | Groups share their board communication (Q2) — vote on which version would have worked best

## Slide 9
04
LOCAL SCENARIO
The
Failed
NGO
Programme
Kenya · Community Health Initiative
A $2M, 3-year community health programme was abandoned in Year 2 after community leaders withdrew support. Donors pulled funding. The NGO had consulted government ministries and international partners — but not the village elders and women's groups who were the primary beneficiaries.
The Stakeholder Failure:
Ignored local power structures:
Village elders and women's groups — the real gatekeepers — were never consulted
Assumed government = community:
Ministry sign-off was treated as community consent — a critical misidentification
One-way communication only:
Programme updates went from NGO to donors — never to beneficiaries
No feedback mechanism:
Field staff raised concerns about community resistance — management dismissed them
Late crisis communication:
When resistance emerged, the NGO communicated defensively rather than collaboratively

## Slide 10
Scenario 04 — The Failed NGO Programme (Kenya)
Your Challenge: Rescue the Programme
ANALYTICAL
Map the stakeholder ecosystem of this programme. Who should have been in each quadrant of the Power/Interest Grid — and who was actually engaged? What does the gap reveal?
💬 Actors: Ministry of Health, donors, village elders, women's groups, field staff, school heads, local health workers, international partners.
CREATIVE
Design a Community Engagement Protocol for this programme's relaunch. It must include: entry process, decision-making hierarchy, communication rhythm, and a red-flag early warning system.
💬 Think practically: How do you enter a community? Who do you speak to first? What does consent look like? How do you know resistance is building?
PROVOCATIVE
The NGO had good intentions, significant funding, and technical expertise — and still failed. Is this a stakeholder management failure, a cultural intelligence failure, or a power dynamics failure? Defend your answer.
💬 There is no single right answer. The strongest teams will argue all three — then prioritise.
⏱ Group Activity — 20 minutes | Present your Community Engagement Protocol (Q2) — class votes on the most implementable design

## Slide 11
What the Cases Have in Common
Across BP, Heathrow T5, Kodak, and the Kenya NGO — the same five patterns emerge:
01
The Right Stakeholders Were Absent
In every case, the people with the most critical information or legitimate interest were excluded from the conversation.
02
Warnings Were Heard But Not Acted On
Internal signals — engineers, field staff, analysts — raised flags. The system had no mechanism to convert warnings into decisions.
03
Communication Was One-Way
Information flowed from leadership outward. No feedback loops meant reality never reached the decision-makers.
04
Power Structures Were Misread
Formal authority was engaged while informal power — elders, engineers, frontline workers — was ignored.
05
Late Engagement Made It Worse
In each case, stakeholders were engaged reactively — after the crisis — not proactively, when they could have prevented it.

## Slide 12
FINAL CHALLENGE
Build Your
Own Case
Working in groups of 3–4, construct a stakeholder management case study from an organisation you know — or one you invent.
1
Name the organisation and the programme
2
Identify at least 6 stakeholders and map them on the P/I Grid
3
Describe one communication failure in the programme
4
Write one analytical and one provocative question for another group
5
Present in 5 minutes — then swap and answer each other's questions
What Makes a Great Case?
Specificity
Name real-ish organisations, roles, and actions — avoid vague generalities
Complexity
The best cases have no obvious villain — failure emerges from a system, not one person
Teachability
Your questions should have no single right answer — they should provoke genuine debate
Dual perspective
Present the failure from TWO stakeholder viewpoints — not just leadership's
The 'so what'
End with a clear lesson that connects to a framework from this module
⏱ 30 minutes total — 20 min build · 5 min present · 5 min Q&A

## Slide 13
Module Reflection
Three Questions to Leave With
01
Think of a programme or project you have worked on or observed. Who was missing from the stakeholder table — and what was the cost of their absence?
02
If you had to introduce one structural change to how your organisation currently manages stakeholders, what would it be — and what resistance would you expect?
03
Stakeholder management is fundamentally about trust. What is one thing you personally commit to doing differently in your next program, starting from tomorrow?
Stakeholder Management Training · Applied Scenarios & Case Studies · End of Module